## Sheet1
Task Name | Start Date | End Date | Duration | Dependencies | Assigned to
Topic Selection | 2026-03-01 | 2026-03-07 | 6 | None | Marcushia N.G.K Marcus-Bangura
Requirement and Concepts | 2026-03-08 | 2026-03-21 | 13 | Topic Selection | Kumba Blessing Fatoma
SLDC Planning | 2026-03-22 | 2026-04-04 | 13 | Requirement | Samuel A Tarawally
System Anlysis (UML) | 2026-04-05 | 2026-04-25 | 20 | SLDC Planning | Kumba Blessing Fatoma
System Architecture | 2026-04-26 | 2026-05-09 | 13 | System Analysis | Samuel A Tarawally
Figma Prototype Design | 2026-05-10 | 2026-05-30 | 20 | System Architecture | Marcushia N.G.K Marcus-Bangura
Testing | 2026-05-31 | 2026-06-13 | 13 | Prototype Design | Kumba Blessing Fatoma
Documentation | 2026-06-14 | 2026-07-15 | 31 | All previous tasks | Marcushia N.G.K Marcus-Bangura